## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Anushka Negi | 2025-11-22 | Initial ASR transcription accuracy was low for noisy audio files and long speech segments. | Sprint-1 | Anushka Negi | Model Accuracy | Added audio preprocessing (resampling + trimming) and tested Whisper with multiple audio samples. | 2025-11-25 | Closed | Transcription accuracy improved significantly.
2 | Anushka Negi | 2025-11-26 | Audio upload failed for unsupported file formats. | Sprint-1 | Anushka Negi | Logical | Implemented strict audio format validation and proper error messages. | 2025-11-27 | Closed | Invalid files now handled gracefully.
3 | Anushka Negi | 2025-12-04 | Transcription processing was slow for long audio inputs. | Sprint-2 | Anushka Negi | Performance | Implemented chunk-based audio processing. | 2025-12-07 | Closed | Reduced processing time for long audios.
4 | Anushka Negi | 2025-12-09 | Subtitle timing mismatch with translated audio playback | Sprint -2 | Anushka Negi | Functional | Fixed timestamp synchronization logic between audio and subtitles | 2025-12-12 | Closed | Audio and subtitles now synced correcttly.
5 | Anushka Negi | 2025-12-16 | Translation quality was inconsistent for some Indian languages. | Sprint-2 | Anushka Negi | Model Accuracy | Tuned NLLB-200 model parameters and tested with diverse language samples. | 2025-12-19 | Closed | Translation quality improved
6 | Anushka Negi | 2025-12-22 | YouTube video audio extraction occasionally failed for certain URLs. | Sprint 3 | Anushka Negi | Integration | Improved FFmpeg based audio extraction and added error handling. | 2025-12-24 | CLosed | Stable YouTube processing achieved.
7 | Anushka Negi | 2025-12-29 | Playback lag observed while merging translated audio with video. | Sprint-3 | Anushka Negi | Performance | Optimized Ffmpeg merge pipeline and buffering logic | 2016-01-01 | Closed | Smooth video playback achieved.
8 | Anushka Negi | 2026-01-02 | Application deployment failed on low RAM environment | Sprint-4 | Anushka Negi | Environment | Handled video and YouTube input separately using yt-dlp and changed Whisper model from base to small.en for better accuracy. | 2026-02-01 | Closed | Working correctly after backend changes and re-tested with audio, video, and YouTube inputs.

## Sheet2
Logical
User Interface
Maintainability
Standards
Environment
Others